## Sheet1
ID | % completed | Task Name | Durations | Start | Finish
| 0% | To Anlyse the doucment and create working envirnment |  | 2023-02-21
|  | Work to Go through data sheet for SHTx | 1.5 | 2023-02-22 | 2023-02-23
|  | Work to go through data sheet for Atmega microcontroller | 1 | 2023-02-23 | 2023-02-24
|  | Work to go through data sheet for Atmega microcontroller for confiurations | 1 | 2023-02-24 | 2023-02-24
|  | Work to prepare flow chart using document shared by client | 1 | 2023-02-27 | 2023-02-28
|  | Work to go through the nextion editor software and analysing it’s working functionality | 1 | 2023-03-01 | 2023-03-02
|  | Work to go through the installation of Arduino IDE and Nextion Editor | 2 | 2023-03-02 | 2023-03-03
|  | Work to understand the behaviour and functionality of the thermostat |  | 2023-03-04 | 2023-03-04